## Sheet1
|  | Development |  |  | Testing
Slide | Tasks | Resource | Start Date | End date | Resource | Start Date | End date
Home Page
| HTML for 1440 | Vikrant / Shrikant | 2013-07-23 | 2013-07-26 | Yogendra | 2013-07-26 | 2013-07-26
| HTML for 1280 | Vikrant / Shrikant | 2013-07-23 | 2013-07-26 | Yogendra | 2013-07-26 | 2013-07-26
| HTML for 1024 | Vikrant / Shrikant | 2013-07-23 | 2013-07-26 | Yogendra | 2013-07-26 | 2013-07-26
| HTML for 768 | Vikrant / Shrikant | 2013-07-23 | 2013-07-26 | Yogendra | 2013-07-26 | 2013-07-26
| Reading Json from Server | Prithi | 2013-07-26 | 2013-07-26 | Yogendra | 2013-07-26 | 2013-07-26
| Storing data in localstorage | Prithi | 2013-07-26 | 2013-07-26 | Yogendra | 2013-07-26 | 2013-07-26
| Binding Header based on Json data | Prithi | 2013-07-26 | 2013-07-26 | Yogendra | 2013-07-26 | 2013-07-26
| Binding Footer based on Json data | Prithi | 2013-07-26 | 2013-07-26 | Yogendra | 2013-07-26 | 2013-07-26
| Showing Lightbox on Footer links with Ajax | Alpesh | 2013-07-26 | 2013-07-26 | Yogendra | 2013-07-26 | 2013-07-26
Shop Plan
| HTML Shop Plan Page | Vikrant / Shrikant | 2013-07-23 | 2013-07-29 | Yogendra | 2013-07-26 | 2013-07-29
| HTML Detailed plan pages - 3 | Vikrant / Shrikant | 2013-07-23 | 2013-07-29 | Yogendra | 2013-07-26 | 2013-07-29
| Nest | Vikrant / Shrikant | 2013-07-23 | 2013-07-29 | Yogendra | 2013-07-26 | 2013-07-29
| Essential | Vikrant / Shrikant | 2013-07-23 | 2013-07-29 | Yogendra | 2013-07-26 | 2013-07-29
| Eagles | Vikrant / Shrikant | 2013-07-23 | 2013-07-29 | Yogendra | 2013-07-26 | 2013-07-29
| Highlighting menu based on Url | Vikrant / Alpesh | 2013-07-26 | 2013-07-26 | Yogendra | 2013-07-26 | 2013-07-29
| Binding Header based on Json data | Prithi | 2013-07-29 | 2013-07-29 | Yogendra | 2013-07-26 | 2013-07-29
| Binding Footer based on Json data | Prithi | 2013-07-29 | 2013-07-29 | Yogendra | 2013-07-26 | 2013-07-29
| Populate STep1 State data from Json / Local Storage | Alpesh | 2013-07-26 | 2013-07-26 | Yogendra | 2013-07-26 | 2013-07-29
| Show tooltip for State help image from Json | Prithi | 2013-07-29 | 2013-07-29 | Yogendra | 2013-07-26 | 2013-07-29
| Populate Utility data of State from Json / Localstorage | Alpesh | 2013-07-26 | 2013-07-26 | Yogendra | 2013-07-26 | 2013-07-29
| Show tooltip for Utility help image from Json | Prithi | 2013-07-29 | 2013-07-29 | Yogendra | 2013-07-26 | 2013-07-29
| Show the bundle data based on State and utility from Json / localstorage | Alpesh | 2013-07-29 | 2013-07-29 | Yogendra | 2013-07-26 | 2013-07-29
| Populate Price | Alpesh | 2013-07-29 | 2013-07-29 | Yogendra | 2013-07-26 | 2013-07-29
| Enable / Disable Enroll Now and Important Offer details links based on state and Utility selection | Prithi | 2013-07-29 | 2013-07-29 | Yogendra | 2013-07-26 | 2013-07-29
changes